## Devops Overview
# | Epic | Status | ETA | % Completed | Sprint 21 Goal | Week - 40 (planned) | Estimated Completion | Remarks / Updates/Achievement
1 | Convergence CI/CD Stabilization – Enable CICD for Ags 2025 All platform with Build optimized approach | Done | 18-Jul -Revised | 100% |  |  |  | CI/CD job is ready.
|  |  | 2025-07-31 |  |  |  |  | CI Jobs are running Daily.
[7 empty] | 2025-09-01 | Report card Tcs enablement – Testing
code signing issue – Debugging
Done , Demo provided to hung.
2 | Modern BIOS | In-Progress | 2025-10-25 |  | - Report card Testing in modern BIOS enabled Platform | - Enabled on Multiple VM and based on free platform |  | Added additional Scope in Epic – report card enablement and PTL Platform Enablement .
[5 empty] | - Parallel job trigger. |  |  | Ithaca Job is created and In place (ags2025)
Report card enabled for tarako LnL (TC -57)
6 CICD Jobs Enabled for Ags2025
2 | eDiags CI/CD Development | Done | 2025-07-22 | 100% |  |  |  | CI/CD pipeline developed.
Demo Completed
Sanity test integration ongoing.
|  |  | 2025-10-30 |  | Enable 2 more Platform For eDiags |  |  | Added additional Scope in Epic
3 | BIOS Connect CI/CD Development | In Progress |  | 70% | Demo Planned |  |  | CD is Completed.
|  |  | 2025-10-25 |  |  |  |  | CI For ags is ready
[7 empty] | 2025-11-01 | BC CI job Development In Progress and signing work in progress.
BC test cases are underdevelopment
4 | GitHub Migration Planning | In Progress | 30 Sep 2025 (TBD) | 35% | Ags 2023 Branch cleanup in progress | AgS 2023 and Ags22 , Ags2021 User and release branch Cleanup |  | GitHub understanding in progress.
|  |  | need to alien with David |  |  |  |  | Branch cleanup initiated. And notified all Ags2025 owner
Plan Strategy in Progress
AGS2025 cleanup Completed for user branches
[7 empty] | 2025-12-01 | Ags2024 cleanup in progress
Release branch cleanup in notified to user
Github POC -wihout as code we tried
Ags2025Release Branch Cleanup – Completed -10-Sep
5 | AGS Sustenance Jenkins Job Stabilization | In Progress | 2025-06-15 | 75% | Sign Server dependency, working on flashing issue | Stability and enabled Platform |  | 18 jobs moved to VM Jenkins and Jobs are running daily
Remaining-11 jobs in Progress .
Old Platform finding in Progress
[7 empty] | 2025-10-01 | 35 platform enabled (12 Sep )- 6 jobs failing because of sign
Optimized build created on ags2024 and Ags2025
| Build Optimizations and enabling all Ags jobs | In-Progress | 2025-10-30 |  |  |  |  | Optimizations and enabling al job
6 | CI/CD Dashboard for Status Visibility | In Progress | 30-Sep-25-> | 70% | Board View update | Dashboard Release |  | CI and CD jobs Status fetching is completed
|  |  | 2025-10-30 |  |  |  | 2025-10-01 | dashboard layout and formatting in progress
Hosting in done on jenkin server and able to access in Dell network
7 | DPF , Dock | In Planning | TBD | 2% | In Planning |  |  | CDRACK Stretogy document in draft Stage
8 | Tristan | In Progress | 2025-09-30 | 75% | BAT Test case enablement and Black duck | 2st Release for Triston | 2025-10-01 | Completed Brickyard and Dover & working oon donnington,Valencia
9 | AI Enhancements for Devops | In Planning | 2025-10-10 |  | Jenkins job creation & to do list creation |  | 2025-12-01 | Created the ideas for implementation AI approches for Devops

## EPIC Details
No | Epic No | Epic Details | Status
1 | BDCD-721 | PR-Based CI/CD Trigger Implementation for Convergence and Modern BIOS Project | Done
2 |  | Modern Bios | In-Progress
3 | BDCD-720 | eDiags CI/CD Development | Done
4 | BDCD-720 | BIOS Connect CI/CD Development | In-Progress
5 | BDCD-716 | Migration from Bitbucket to GitHub | In-Progress
6 | BDCD-635 | AGS Sustenance Jenkins Job Stabilization | In-Progress
7 |  | Build Optimizations and enabling all Ags jobs | In-Progress
8 | BDCD-636 | CI/CD Dashboard for Status Visibility | In-Progress
9 | CCBC-224 | Tristan CICD | In-Progress
10 |  | AI Enhancements for Devops | In-Planning

## Tristan
No | Task Number | Tristan CICD task details | Status | Completion
1 | CCBC-226 | CICD end to end implementation for tristan and future enhancements to Github action | Done | 2025-10-01
2 | CCBC-227 | Branching strategy for code integration,PR and Build requirements | Done
3 | CCBC-228 | Hardware readiness for cicd activities | Done
4 | CCBC-229 | CI/CD pipeline for BIOS (Jenkins/Bitbucket) | Done
5 | CCBC-230 | Enable email alerts and share commit information of the submodule in Bitbucket with the end users and the watcher list
6 | CCBC-231 | Create a JIRA ticket automatically based on commit information from Bitbucket
7 | CCBC-232 | CI/CD pipeline for cDRAC
8 | CCBC-233 | Artifactory linking of build files | In-Progress
9 | CCBC-234 | Signing job creation for BIOS | Done
10 | CCBC-235 | Monitoring Dashboard - BIOS | Done
11 | CCBC-236 | Adding Coverity to pipeline - BIOS
12 | CCBC-237 | Adding Blackduck to pipeline - BIOS
13 | CCBC-238 | Integration Testing the CI/CD pipelines
14 | CCBC-239 | Alignment with NPI Team
15 | CCBC-240 | Migration : Job Migration once github in place for ags2024
16 | CCBC-242 | Build CICD for Valencia platform | In-Progress
17 | CCBC-243 | Set up the alert metrics for cicd | In-Progress
18 | CCBC-244 | Build CICD for Donnington platform | In-Progress
19 | CCBC-245 | Build the stability of jenkins pipeline for cicd | In-Progress

## AI
No | Task Detail | Start Date | End Date
1 | AI-Driven Approaches to Run Similar Jenkins Jobs | 2025-10-01 | 2025-12-01
2 | AI-Powered To-Do List Activities | 2025-11-01 | 2026-01-01