## Devops Overview
# | Epic | Status | ETA | % Completed | Sprint 21 Goal | Week - 40 (planned) | Estimated Completion | Remarks / Updates/Achievement
1 | Convergence CI/CD Stabilization – Enable CICD for Ags 2025 All platform with Build optimized approach | Done | 18-Jul -Revised | 100% |  |  |  | CI/CD job is ready.
|  |  | 2025-07-31 |  |  |  |  | CI Jobs are running Daily.
[7 empty] | 2025-09-01 | Report card Tcs enablement – Testing
code signing issue – Debugging
Done , Demo provided to hung.
2 | Modern BIOS | In-Progress | 2025-10-25 |  | - Report card Testing in modern BIOS enabled Platform | - Enabled on Multiple VM and based on free platform |  | Added additional Scope in Epic – report card enablement and PTL Platform Enablement .
[5 empty] | - Parallel job trigger. |  |  | Ithaca Job is created and In place (ags2025)
Report card enabled for tarako LnL (TC -57)
6 CICD Jobs Enabled for Ags2025
2 | eDiags CI/CD Development | Done | 2025-07-22 | 100% |  |  |  | CI/CD pipeline developed.
Demo Completed
Sanity test integration ongoing.
|  |  | 2025-10-30 |  | Enable 2 more Platform For eDiags |  |  | Added additional Scope in Epic
3 | BIOS Connect CI/CD Development | In Progress |  | 70% | Demo Planned |  |  | CD is Completed.
|  |  | 2025-10-25 |  |  |  |  | CI For ags is ready
[7 empty] | 2025-11-01 | BC CI job Development In Progress and signing work in progress.
BC test cases are underdevelopment
4 | GitHub Migration Planning | In Progress | 30 Sep 2025 (TBD) | 35% | Ags 2023 Branch cleanup in progress | AgS 2023 and Ags22 , Ags2021 User and release branch Cleanup |  | GitHub understanding in progress.
|  |  | need to alien with David |  |  |  |  | Branch cleanup initiated. And notified all Ags2025 owner
Plan Strategy in Progress
AGS2025 cleanup Completed for user branches
[7 empty] | 2025-12-01 | Ags2024 cleanup in progress
Release branch cleanup in notified to user
Github POC -wihout as code we tried
Ags2025Release Branch Cleanup – Completed -10-Sep
5 | AGS Sustenance Jenkins Job Stabilization | In Progress | 2025-06-15 | 75% | Sign Server dependency, working on flashing issue | Stability and enabled Platform |  | 18 jobs moved to VM Jenkins and Jobs are running daily
Remaining-11 jobs in Progress .
Old Platform finding in Progress
[7 empty] | 2025-10-01 | 35 platform enabled (12 Sep )- 6 jobs failing because of sign
Optimized build created on ags2024 and Ags2025
| Build Optimizations and enabling all Ags jobs | In-Progress | 2025-10-30 |  |  |  |  | Optimizations and enabling al job
6 | CI/CD Dashboard for Status Visibility | In Progress | 30-Sep-25-> | 70% | Board View update | Dashboard Release |  | CI and CD jobs Status fetching is completed
|  |  | 2025-10-30 |  |  |  | 2025-10-01 | dashboard layout and formatting in progress
Hosting in done on jenkin server and able to access in Dell network
7 | DPF , Dock | In Planning | TBD | 2% | In Planning |  |  | CDRACK Stretogy document in draft Stage
8 | Tristan | In Progress | 2025-09-30 | 75% | BAT Test case enablement and Black duck | 2st Release for Triston | 2025-10-01 | Completed Brickyard and Dover & working oon donnington,Valencia
9 | AI Enhancements for Devops | In Planning | 2025-10-10 |  | Jenkins job creation & to do list creation |  | 2025-12-01 | Created the ideas for implementation AI approches for Devops

## EPIC Details
# | Epic No | Epic | Status
1 |  | Convergence CI/CD Stabilization – Enable CICD for Ags 2025 All platform with Build optimized approach | Done
BDCD-721
2 |  | Modern BIOS | In-Progress
2 |  | eDiags CI/CD Development | Done
BDCD-720
3 |  | BIOS Connect CI/CD Development | In Progress
BDCD-720
4 |  | GitHub Migration Planning | In Progress
BDCD-716
5 |  | AGS Sustenance Jenkins Job Stabilization | In Progress
BDCD-635
|  | Build Optimizations and enabling all Ags jobs | In-Progress
6 |  | CI/CD Dashboard for Status Visibility | In Progress
BDCD-636
7 |  | DPF , Dock | In Planning
8 | CCBC-224 | Tristan | In Progress
9 |  | AI Enhancements for Devops | In Planning

## Tristan
Tr

## Sheet5
ETA | Sprint 21 Goal | Average of % Completed
18-Jul -Revised | (blank) | 100%
18-Jul -Revised Total |  | 100%
30 Sep 2025 (TBD) | Ags 2023 Branch cleanup in progress | 35%
30 Sep 2025 (TBD) Total |  | 35%
30-Sep-25-> | Board View update | 70%
30-Sep-25-> Total |  | 70%
need to alien with Devid | (blank)
need to alien with Devid Total
TBD | In Planning | 2%
TBD Total |  | 2%
2025-06-15 | Sign Server dependency, working on flashing issue | 75%
15-06-2025 Total |  | 75%
2025-07-22 | (blank) | 100%
22-07-2025 Total |  | 100%
2025-07-31 | (blank)
31-07-2025 Total
2025-09-30 | BAT Test case enablement and Black duck | 75%
30-09-2025 Total |  | 75%
2025-10-25 | (blank)
- Report card Testing in modern BIOS enabled Platform
25-10-2025 Total
2025-10-30 | (blank)
Enable 2 more Platform For eDiags
30-10-2025 Total
(blank) | Demo Planned | 70%
(blank)
- Parallel job trigger.
(blank) Total |  | 70%
Grand Total |  | 65.88%

## Sheet6
Status | Count of #
In Progress | 4
In Planning | 2
Done | 2
(blank)
In-Progress
Grand Total | 8

## Sheet7
No | Epic No | Epic Details | Status
| BDCD-721 | PR-Based CI/CD Trigger Implementation for Convergence and Modern BIOS Project

## Sheet8
Status | Count of #
In Progress | 5
In Planning | 2
Done | 2
In-Progress | 1
(blank)
Grand Total | 10