## Sheet1
Category | Details
Project Info | Tristan Use Case - Started on 1 Sep 2025
Platform Completion | Dover, Brickyard - Completed 30 Sep; Valencia, Donning - Expected 14 Oct
Test Case Enablement | BAT Regression - Enabled on Tristan Dev Branch; 22 BATs enabled; Regression testing not started
Build Jobs | Schedule-based build job execution implemented
Signing Execution | Code signing and execution process integrated with CI/CD pipeline
Integration & Automation | EC Integration & BIOS automation workflows initiated
Tools Configuration | Blackduck and Coverity tools configured for Tristan; security scan automation integrated
Migration Readiness | Migration readiness achieved with full resource allocation (100%)
Resource Allocation | Vijay - CI/CD; Karthik - CI & Cleaning; Muni - CI/CD & Automation; Ishika - CI/CD & Monitoring
Current Sprint Tasks | Ongoing sprint focuses on CI/CD improvements, cleaning, and automation enhancement
Future Timeline (till 2025) | Detailed plan for CI/CD standardization across multiple platforms, cleaning, migration, and build stability improvements by end of 2025