## Consolidated Summary
Category | Details
Use Case | Tristan
Start Date | 2025-09-01
Target Completion | 2025-10-14
Overall Status | In Progress
Platform Completion Summary | Dover, Brickyard: Completed 30-Sep-2025; Valencia, Donning: Expected 14-Oct-2025
Primary Scope | CI/CD Enablement, Platform Migration, Build Stability, Automation, Tool Integration
Tools Involved | Jenkins, Bitbucket, BlackDuck, Coverity, ECIntegration, BIOS Automation
Resources Allocated | 4 Members (100% Utilization)
Sprint Focus (Current) | CI/CD Stabilization, Cleaning, Migration Readiness, Build Scheduling, Regression Automation
Next Milestones | Regression Start; Valencia-Donning Platform Completion; BlackDuck Integration Validation
Reporting Owner | Thangasamy Ganesan
Last Updated | 2025-10-09

## Platform Progress
Platform | Start Date | Planned Completion | Actual/Expected Completion | Status | Comments
Dover | 2025-09-01 | 2025-09-30 | 2025-09-30 | Completed | Delivered successfully
Brickyard | 2025-09-01 | 2025-09-30 | 2025-09-30 | Completed | Build validated
Valencia | 2025-10-01 | 2025-10-14 | 2025-10-14 (Expected) | In Progress | Final testing pending
Donning | 2025-10-01 | 2025-10-14 | 2025-10-14 (Expected) | In Progress | Awaiting regression results

## CI_CD & Automation
Area | Description | Status | Owner | Notes
BAT Test Enablement | 22 BAT cases enabled for Tristan dev branch | Completed | Muni | Regression pending
Regression Testing | Full regression cycle | Not Started | Ishika | Planned post 14-Oct
Build Jobs | Schedule-based builds configured | Completed | Vijay | Nightly trigger setup
Signing Execution | Signing flow setup for build output | In Progress | Vijay | Integration with EC BIOS pending
ECIntegration / BIOS Automation | Automation of BIOS test flow | In Progress | Muni | Validation scripts under testing
BlackDuck Configuration | Open-source scan tool setup | Completed | Karthik | Integration verified
Coverity Configuration | Static code analysis setup | Completed | Karthik | Scan results in Jenkins dashboard
Migration Readiness | Platform migration prepared | Ready | Team | Scheduled for next phase

## Resource Allocation
Resource | Allocation % | Key Responsibilities | Current Sprint Focus
Vijay | 100% | CI/CD, Build Scheduling | Build Jobs, Signing Flow
Karthik | 100% | CI, Cleaning, Code Quality | BlackDuck, Coverity, Cleaning
Muni | 100% | CI/CD, Automation | BAT Test Enablement, ECIntegration
Ishika | 100% | CI/CD, Monitoring | Regression Planning, Build Validation

## Sprint Plan
Sprint | Duration | Goals | Deliverables | Status
Sprint 1 | 2025-09-01 to 2025-09-15 | Initial CI/CD Setup | Jenkins pipelines, Bitbucket link | Completed
Sprint 2 | 2025-09-16 to 2025-09-30 | Platform Build & Validation | Dover, Brickyard platform build | Completed
Sprint 3 | 2025-10-01 to 2025-10-14 | Regression & Automation Setup | Valencia & Donning completion, Regression enablement | In Progress
Sprint 4 | 2025-10-15 to 2025-10-31 | Migration Readiness | Full toolchain validation, Stability report | Planned

## Timeline
Task | Start Date | End Date | Owner | Status
Platform Setup (Dover, Brickyard) | 2025-09-01 | 2025-09-30 | Team | Completed
Platform Setup (Valencia, Donning) | 2025-10-01 | 2025-10-14 | Team | In Progress
BAT Enablement | 2025-09-20 | 2025-09-25 | Muni | Completed
Regression Enablement | 2025-10-15 | 2025-10-25 | Ishika | Planned
Build Job Scheduling | 2025-09-10 | 2025-09-20 | Vijay | Completed
Signing Execution | 2025-09-25 | 2025-10-15 | Vijay | In Progress
Tool Integration (BlackDuck/Coverity) | 2025-09-15 | 2025-09-30 | Karthik | Completed
Migration Preparation | 2025-10-01 | 2025-10-31 | Team | Ongoing

## Status Summary
Status | Count
Completed | 2
In Progress | 1
Planned | 1