## Roadmap
Phase | Description | Start Date | End Date | Status
Modern BIOS | Modern BIOS development and integration | 2025-09-01 | 2025-09-15 | Planned
Tools Implementation | Implement development and testing tools | 2025-09-16 | 2025-09-25 | Planned
Cleanup | Code and environment cleanup | 2025-09-26 | 2025-09-30 | Planned
AGS Optimization | Optimize AGS performance | 2025-10-01 | 2025-10-07 | Planned
GitHub Actions | Setup CI/CD pipelines using GitHub Actions | 2025-10-08 | 2025-10-14 | Planned
Phase | Duration
Modern BIOS | 14
Tools Implementation | 10
Cleanup | 5
AGS Optimization | 7
GitHub Actions | 7

## Platform Status
Platform | Status | Completion Date
Dover | Completed | 2025-09-30
Brickyard | Completed | 2025-09-30
Valencia | Expected | 2025-10-14
Donning | Expected | 2025-10-14

## Resource Allocation
Name | Role | Assigned Tasks
Vijay | Developer | Modern BIOS, Cleanup
Karthik | Tester | Tools Implementation, AGS Optimization
Muni | DevOps | GitHub Actions
Ishika | Project Manager | Coordination, Reporting