## Sheet1
| Status | ETA | % Completed | Sprint 21 Goal | Week - 40 (planned) | Remarks / Updates/Achievement
Epic
1 | Convergence CI/CD Stabilization – Enable CICD for Ags 2025 All platform with Build optimized approach | Done | 18-Jul -Revised | 100% |  |  | CI/CD job is ready.
|  |  | 2025-07-31 |  |  |  | CI Jobs are running Daily.
Report card Tcs enablement – Testing
code signing issue – Debugging
Done , Demo provided to hung.
| Modern BIOS | In-Progress | 2025-10-25 |  | - Report card Testing in modern BIOS enabled Platform | - Enabled on Multiple VM and based on free platform | Added additional Scope in Epic – report card enablement and PTL Platform Enablement .
[5 empty] | - Parallel job trigger. |  | Ithaca Job is created and In place (ags2025)
Report card enabled for tarako LnL (TC -57)
6 CICD Jobs Enabled for Ags2025
2 | eDiags CI/CD Development | Done | 2025-07-22 | 100% |  |  | CI/CD pipeline developed.
Demo Completed
Sanity test integration ongoing.
|  |  | 2025-10-30 |  | Enable 2 more Platform For eDiags |  | Added additional Scope in Epic
3 | BIOS Connect CI/CD Development | In Progress |  | 70% | Demo Planned |  | CD is Completed.
|  |  | 2025-10-25 |  |  |  | CI For ags is ready
BC CI job Development In Progress and signing work in progress.
BC test cases are underdevelopment
4 | GitHub Migration Planning | In Progress | 30 Sep 2025 (TBD) | 35% | Ags 2023 Branch cleanup in progress | AgS 2023 and Ags22 , Ags2021 User and release branch Cleanup | GitHub understanding in progress.
|  |  | need to alien with Devid |  |  |  | Branch cleanup initiated. And notified all Ags2025 owner
Plan Strategy in Progress
AGS2025 cleanup Completed for user branches
Ags2024 cleanup in progress
Release branch cleanup in notified to user
Github POC -wihout as code we tried
Ags2025Release Branch Cleanup – Completed -10-Sep
5 | AGS Sustenance Jenkins Job Stabilization | In Progress | 2025-06-15 | 75% | Sign Server dependency, working on flashing issue | Stability and enabled Platform | 18 jobs moved to VM Jenkins and Jobs are running daily
Remaining-11 jobs in Progress .
Old Platform finding in Progress
35 platform enabled (12 Sep )- 6 jobs failing because of sign
Optimized build created on ags2024 and Ags2025
| Build Optimizations and enabling all Ags jobs | In-Progress | 2025-10-30 |  |  |  | Optimizations and enabling al job
6 | CI/CD Dashboard for Status Visibility | In Progress | 30-Sep-25-> | 70% | Board View update | Dashboard Release | CI and CD jobs Status fetching is completed
|  |  | 2025-10-30 |  |  |  | dashboard layout and formatting in progress
Hosting in done on jenkin server and able to access in Dell network
7 | DPF , Dock | In Planning | TBD | 2% | In Planning |  | CDRACK Stretogy document in draft Stage
8 | Triston | In Planning | 2025-09-30 | 75% | BAT Test case enablement and Black duck | 2st Release for Triston | Created plan and working on understanding build
3 Jobs for triston – Dover and brickyard – CI and CD job enabled
1st release completed for Triston